## MU Coordinator - MSC
User: Cindy Moon
Username: cmoon1234
Password: mtrx1234
Division (Company): Matrix PDM
Testing Security Role: MU Coordinator - MSC
# | Role | Task | Steps | Inputs/Data | Expected Results | Actual Results | Pass/Fail | Date Tested | Questions/Comments (UAT Tester) | Resolution/Notes (Reserved for UAT Admin)
2.1 | MU Coordinator - MSC | Create a certification family | 1. From the Welcome page, place the cursor over the Admin navigation tab and select Catalog. 2. Click Certifications. 3. Click Manage Families and Categories. 4. Click Add New Certification Family. 5. Enter the family name in the newly generated field. 6. Click the save icon to the right of the field. | • Create one (1) family. | • Certification family is created.
2.2 | MU Coordinator - MSC | Create a certification category | 1. From the Welcome page, place the cursor over the Admin navigation tab and select Catalog. 2. Click Certifications. 3. Click Manage Families and Categories. 4. Click the Categories tab. 5. Click Add New Certification Category. 6. Enter the category name in the newly generated field. 7. Click the save icon to the right of the field. | • Create one (1) category. | • Certification category is created.
2.3 | MU Coordinator - MSC | Build a certification | 1. From the Welcome page, place the cursor over the Admin navigation tab and select Catalog. 2. Click Certifications. 3. Click Create a New Certification. General 4. Enter the certification name in the Title field. 5. Enter an explanation of the certification in the Description field. 6. Select the appropriate Family for the certification from the drop-down options. 7. Select the appropriate Category for the certification from the drop-down options. 8. Add a Training Contact by clicking the new window icon. 9. Enter the last name of the user you wish to add in the Last Name field. 10. Click Search. 11. Click the name of the user. 12. Verify the Active checkbox is checked. 13. Under the Details section, click checkboxes to select the appropriate options. 14. Under the Availability heading, select All Users from the Select OU Criteria drop-down options. 15. Click Add. 16. Click Next. Framework 17. Click the Add Section icon under the Options heading. 18. Enter the section name in the Title field. 19. Enter the required credits for the section in the Min and Max fields. 20. Click OK. | • Date for Initial Certification: Last training item completion date • Detail Options: • Allow users to add extenal training • Delegate approval process of external training to user's manager • Override LO Availability • Allow users to print certificate upon completion • Allow training items to recur ignoring the recurrence setting on training level. • Users are required to complete the minimum credits for all child sections in order for credits to be counted towards the parent section. • Change tracking unit from credit to CEU • Select OU Criteria: All Users • Section Title: Initial Certification • Min and Max Credit Requirements: 20; 20 • Section Title: Certification Renewal • Min and Max Credit Requirements: 10; 10 | • Certification is built.
21. Click Add Item. 22. Click Add Training. 23. Check the boxes for all learning object types you wish to search. 24. Enter the name of the LO you wish to add in the Title field. 25, Click Search. 26. Click the add icon to the left of the LO title. 27. Click Done. 28. Repeat steps #22-27 to add additional learning objects. 29. Order the sequence of the LOs by entering a sequence number for each LO inthe Sequence field. 30. Enter the credits for each LO in the field. Note: The heading for this field is determined by what was entered as the tracking unit in the General settings. 31. Click Next. Scheduling 32. To begin to schedule the period, click the new window icon to the right of the Certification Period Title. 33. Click the radial for the appropriate Certification Period Selection. 34. Click Select. 35. Enter the name for the period in the Certification Period Title field. 36. Enter the required credits. 37. To select the appropriate sections(s) for the period, click the checkbox to the left of the section name. 38. Click Select. 39. Click the Period Date icon on the period box. 40. Enter the appropriate Due Date and Expiration Date on the Configure Certification Period pop-up window. 41. Click Select.
42. To add a renewal period, click the add icon to the right of the Create Certification Schedule heading. 43. Enter the name for the period in the Certification Period Title field. 44. Enter the required credits. 45. To select the appropriate sections(s) for the period, click the checkbox to the left of the section name. 46. Click the appropriate Details checkboxes. 47. To select the appropriate sections(s) for the period, click the checkbox to the left of the section name. 48. Click Select. 49. Click the Period Date icon on the period box. 50. Enter the appropriate date information on the Configure Certification Period pop-up window. Note: Duration information is required. 51. Click Select. 52. Click Next. Emails 53. Leave the email selection at the default of System Defaults. 54. Click Next. Confirm 55. Verify the details of the certification. Click Back to make any necessary changes on previous screens. 56. Click Save. 57. Verify the certification appears on the Manage Certifications page.
2.4 | MU Coordinator - MSC | Proxy enroll users into a certification | 1. From the Welcome page, place the cursor over the Admin navigation tab and select Proxy Enrollment. 2. On the Proxy Enrollment page, click the Certification tab. 3. Click Proxy Enrollment for Certification. 4. Click the Add New Users icon to the right of the certification you wish to enroll. 5. Leave the Enrollment selection at the default of Standard. 6. Leave the Assignment selection at the default of Immediately. 7. Skip the Schedule Proxy section. 8. Under the Status heading, click the Assign & Approve Certification radial. 9. Under the Select Users heading, select Users from the Select OU Criteria drop-down options. 10. Click the new window icon. 11. Enter the last name of the user you wish to enroll in the Last Name field. 12. Click Search. 13. Click the name of the user. Verify the user(s) appear under the Select Users heading. 14. Click Next. 15. Verify the details of the enrollment. Click Back to make any necessary changes on previous screens. 16. Click Submit. 17. Click the Certification tab and verify the enrollment. Note: The certification proxy enrollment will initially appear in a Queued status. | User: Samuel Guthrie | • User is enrolled in certification.
2.5 | MU Coordinator - MSC | Approve a certification enrollment | 1. From the Welcome page, place the cursor over the Certification navigation tab and select Certification Management. 2. Click Manage Pending Requests. 3. Click the Approve icon under the Options heading. 4. Enter comments explaining the approval in the Approve Request comments box. 5. Click Submit. | User: Nick Fury Certification: Sample Cert G - GMS | • Certification request is approved.
2.6 | MU Coordinator - MSC | Deny a certification enrollment | 1. From the Welcome page, place the cursor over the Certification navigation tab and select Certification Management. 2. Click Manage Pending Requests. 3. Click the Deny icon under the Options heading. 4. Enter comments explaining the denial in the Deny Request comments box. 5. Click Submit. | User: Ivan Vanko Certification: Sample Cert G - GMS | • Certification request is denied.
2.7 | MU Coordinator - MSC | Remove a certification from a user's transcript | 1. From the Welcome page, place the cursor over the Certification navigation tab and select Certification Management. 2. Click the View Users icon under the Options heading. 3. Click the Delete icon (trashcan) under the Options heading to the right of the user for whom you wish to remove the certification. 4. Click OK on the pop-up message box. | User: Regan Wyngarde Certification: Certification: Sample Cert A - GMS 1 | • Certification is removed from user's transcript.
2.8 | MU Coordinator - MSC | Reversion a certification | 1. From the Welcome page, place the cursor over the Admin navigation tab and select Catalog. 2. Click Certifications. 3. Click the Edit icon to the right of the certification you wish to revise. 4. Use the links in the Edit Certification navigation pane to the left of the page to select the Framework section. 5. Make the appropriate changes to the certificaiton. Note: The following changes will cause a reversioning of the certification - adding new training, removing training, changing the sequence of items within a section, changing credits of a section or training item, and adding or deleting a section. 6. Click Save. 7. On the Versioning page, select the appropriate radial for the users to whom you want the changes to apply. 8. Enter comments to explain the reversion in the Comments box. 9. Click Save. 10. Verify the version number has changed on the Manage Certifications page. | Certification: certification created in task #2.3 | • Certification is updated and a new version is created.

## MU Certification Owner
User: Betty Ross
Username: bross1234
Password: mtrx1234
Division (Company): Matrix PDM
Testing Security Role: MU Certification Owner
# | Role | Task | Steps | Inputs/Data | Expected Results | Actual Results | Pass/Fail | Date Tested | Questions/Comments (UAT Tester) | Resolution/Notes (Reserved for UAT Admin)
2.1 | MU Certification Owner | Approve a certification enrollment | 1. From the Welcome page, place the cursor over the Certification navigation tab and select Certification Management. 2. Click Manage Pending Requests. 3. Click the Approve icon under the Options heading. 4. Enter comments explaining the approval in the Approve Request comments box. 5. Click Submit. | User: Hisako Ichiki Certification: Sample Cert G - GMS | • Certification request is approved.
2.2 | MU Certification Owner | Deny a certification enrollment | 1. From the Welcome page, place the cursor over the Certification navigation tab and select Certification Management. 2. Click Manage Pending Requests. 3. Click the Deny icon under the Options heading. 4. Enter comments explaining the denial in the Deny Request comments box. 5. Click Submit. | User: Luke Cage Certification: Sample Cert G - GMS | • Certification request is denied.

## MU Manager
User: Reed Richards
Username: rrichards1234
Password: mtrx1234
Division (Company): Matrix Service Company
Testing Security Role: MU Manager
# | Role | Task | Steps | Inputs/Data | Expected Results | Actual Results | Pass/Fail | Date Tested | Questions/Comments (UAT Tester) | Resolution/Notes (Reserved for UAT Admin)
2.1 | MU Manager | Assign a certification | 1. From the Welcome page, place the cursor over the Home navigation tab and select Global Search. 2. Click Certifications on the navigation pane to the left of the page. 3. If the desired certification is not visible in the displayed results, click the Refine Search link under the Search field. 4. Enter relevant search information to locate the certification and click Refine. 5. Click the name of the certification in the results. 6. Click Assign. 7. Enter comments as necessary for the assignment. 8. Click the checkbox to the left of the emploiyee to who you wish to assign the certification. 9. Click Submit at the bottom of the page. 10. Verify the assignment by access the employee's transcript through your Universal Profile. a. From the Welcome page, place the cursor over the Home navigation tab and select Universal Profile. b. Scroll to the Team section. c. Click the name of the employee to whom you assigned the certification. d. Click Transcript in the navigation pane to the left of the page. e. Verify the certification appears on the employee's transcript. | Employee: Susan Storm Certification: Sample Cert B - GMS | • User is assigned certification.
2.2 | MU Manager | View an employee's certification on the transcript | 1. From the Welcome page, place the cursor over the Home navigation tab and select Universal Profile. 2. Scroll down to the Team section. 3. Click the name of the employee for whom you wish to view the transcript. 4. Click Transcript on the navigation pane to the left of the page. 5. Locate the certification on the transcript. 6. Click Manage to the right of the certification name. 7. Review the details of the certification. 8. To view progress for the certification, click the Progress Report link in the upper right corner of the page. 9. Click Close on the Progress Report window. | Employee: Ben Grimm Certification: Sample Cert A - GMS 1 | • Certification is reviewed through the user's transcript.

## MU Default User
User: William Worthington
Username: wworthington1234
Password: mtrx1234
Division (Company): Matrix Service, Inc
Testing Security Role: MU Default User
# | Role | Task | Steps | Inputs/Data | Expected Results | Actual Results | Pass/Fail | Date Tested | Questions/Comments (UAT Tester) | Resolution/Notes (Reserved for UAT Admin)
2.1 | MU Default User | Access a certification | 1. From the Welcome page, click the Transcript button. 2. Click Manage to the right of the certification you wish to view. 3. Review the Certification details. | Certification: Sample Cert B - GMS | • Certification is accessed through the transcript.
2.2 | MU Default User | Add external training to a certification | 1. From the Welcome page, click the Transcript button. 2. Click Manage to the right of the certification to which you want to add training. 3. Click Add New External Training. 4. Enter the appropriate information for the external training event. Note: Title, Training Description, Institution,Training Dates (From and To), Training Hours, Apply Credits To, and Requested [Credits] are required. 5. Click OK. 6. Click Mark Complete under the Options heading to the right of the external training just added. 7. Check the acknowledgement statement checkbox and enter Grade Earned information if necessary. 8. Click Submit. 9. Verify the external training item entered a Pending Completion Approval status. | Certification: Sample Cert B - GMS | • External training is added to a certification.
2.3 | MU Default User | Print certificate for a completed certification | 1. From the Welcome page, click the Transcript button. 2. Click Manage to the right of the certification you wish to view. 3. Click the Print Certificate link to the upper right of the page. 4. The certificate will appear as a PDF in a new window. Print as you would any PDF file. | Certification: Sample Cert A - GMS 1 | • Certificate is made available for printing for a completed certification.