## MU Competency Support - HR
User: Wilson Fisk
Username: wfisk1234
Password: mtrx1234
Division (Company): Matrix PDM
Testing Security Role: MU Competency Support - HR
# | Role | Task | Steps | Inputs/Data | Expected Results | Actual Results | Pass/Fail | Date Tested | Questions/Comments (UAT Tester) | Resolution/Notes (Reserved for UAT Admin)
1.1 | MU Competency Support - HR | Create a competency category type and categories | 1. From the Welcome page, place the cursor over the Admin navigation tab and select Performance. 2. Click Competency Bank. 3. Click Define Competency Categories. 4. Click Add Category Type. 5. Enter the category type in the Name field under the Define Category Type heading. 6. Click Add Category. 7. Enter the category in the newly created field. 8. Verify the category is checked Active. 9. Repeat steps #6-8 to create additional categories. 10. Enter the appropriate order numbers in the Order field for each category. 11. Click Update Order. 12. Click Save. 13. Verify the category type has been created on the Define Competency Category Types page. | • Create one (1) category type. • Create three (3) categories type. | • Category type is created. • At least three (3) categories are created.
1.2 | MU Competency Support - HR | Create a competency (Competency Item) | 1. From the Welcome page, place the cursor over the Admin navigation tab and select Performance. 2. Click Competency Bank. 3. Click Create New Competency. 4. Enter the competency in the Name field. 5. Enter a competency description as necessary in the Description field. 6. Enter a unique identifier in the ID field. 7. Select Competency Item from the Assessment Type drop-down options. 8. Select the appropriate category as necessary from the category type drop-down(s). 9. Click the Add Comment link to provide suggested feedback for the competency. 10. Enter the suggested feedback in the Comments textbox on the Suggested Feedback for Competency page. 11. Select the appropriate Category from the drop-down options. 12. Click Save. 13. Repeat steps #9-12 to add addtional comments. | • Create at least three (3) competencies with associated LOs. | • At least three (3) competencies are created.
14. To associate learning obejct(s) (LO) with the competency, click the Add Development Actions to Competency link. 15. Enter the appropriate LO title in the Search by Title or Keyword field. 16. Click Search. 17. Click the add icon to the left of the LO title. 18. Click Done. 19. Leave the Min Rating and Max Rating fields at the default. 20. Click Add Item. 21. Enter the competency item (skill/behvaior) in the text box. 22. Click the save icon to the right of the text box. 23. Repeat steps #20-22 to add additional competency items. 24. Click Submit. 25. Verify the competency appears in the Competency Bank page.
1.3 | MU Competency Support - HR | Create a competency model category | 1. From the Welcome page, place the cursor over the Admin navigation tab and select Performance. 2. Click Competency Assessment Models. 3. Click Define Model Category. 4. Click Add New Category. 5. Enter the category in the Name field under the Category heading. 6. Select the parent category from the Parent drop-down options. 7. Click the save icon. 8. Verify the model categoryhas been created on the Define Categories page. 9. Click Done. | • Create one (1) category. | cCompetency model category is created.
1.4 | MU Competency Support - HR | Create a competency model | 1. From the Welcome page, place the cursor over the Admin navigation tab and select Performance. 2. Click Competency Assessment Models. 3. Click Create New Competency Model. 4. Enter the model name in the Name field. 5. Enter a competency model description as necessary in the Description field. 6. Click the new window icon to the right of Model Category. 7. Select the appropriate model category by clicking the name of the category. 8. Select the appropriate availability form the Select OU Criteria drop-down options. 9. Click the new window icon to the right of the criteria. 10. Click the expand plus (+) sign as needed to locate the appropriate criteria designation. 11. Click the add icon to the left of the appropriate criteria designation. 20. Click Done. 21. Leave the Group By Category Type at the default of None. 22.Click Add Competency. | • Create one (1) competency model using the competencies created in task #1.2. | • Competency model is created.
23. Select a competency for inclusion in the model by clicking the checkbox to the left of the competency ID. 24. Repeat step #23 to select all competencies for the model. 25. Click Done. 26. Use the green Move Up and Move Down arrows to reorder the compatencies. 27. Enter the target rating for the competency in the Target field. Note: This number indicates the rating the person being assessed on this competency should achieve to show at target. 28. Click Submit. 29. Verify the model was created under the Manage Checklists heading.
1.5 | MU Competency Support - HR | Create observation checklist | 1. From the Welcome page, place the cursor over the Admin navigation tab and select Performance. 2. Click Observation Checklists. 3. Click Create New Checklist. General 4. To select the competency model for the checklist, click the new window icon to the right of the Competency Model field. 5. Click the name of the model you wish to use with the checklist. 6. Select a change schema by clicking the appropriate Competency Changes radial button. 7. Click the Define Name radial button. 8. Enter the name in the newly generated field. 9. Click the Define Description radial button. 10. Enter the name in the newly generated text box. 11. Click the checkbox to Expand checklist items by default. 12. Click Allow Notes checkboxes for appropriate users. | • Comptency Model: model from task #1.3 • Allow Notes for: Manager, Verifier, and User. • Attachments for: Manager and Verifier. • Validation: Allow User's Manager to validate; Allow User's Manager to define additional users to validate • Availability: Users Jessica Drew | Observation checklist is created from task #1.3 competency model.
13. Click Attachments checkboxes for appropriate users. 14. Click the checkbox to include a rating scale for every item on the checklist. 15. Click Next. Preferences 16. Leave the checklist Type at the default of Standard. 17. Leave the Due Date at the default of Immediately. 18. Leave the timeframe validated competencies at the default of Always Valid. 19. Select the appropriate availability from the Select OU Criteria drop-down options. 20. Under the Validation heading, select the appropriate roles to complete the observation checklist.
21. Leave the Approval checkbox for Required User's Manager approval unchecked. 22. Click Next. Email 24. Select the appropriate radial for email notification distribution. 25. Click Next. Confirm 26. Review the observation checklist details. Click Save. 27. Verify the checklist appears on the Checklist Administration page. 28. Click Save.

## MU Checklist Verifier
User: Sharon Carter
Username: scarter1234
Password: mtrx1234
Division (Company): Matrix NAC
Testing Security Role: MU Checklist Verifier
# | Role | Task | Steps | Inputs/Data | Expected Results | Actual Results | Pass/Fail | Date Tested | Questions/Comments (UAT Tester) | Resolution/Notes (Reserved for UAT Admin)
1.1 | MU Checklist Verifier | Administer an observation checklist | 1. From the Welcome page, place the cursor over the Checklists navigation tab and select Manage Checklists. 2. Under the Search Users heading, locate the appropriate user for whom you will verify a checklist. 3. Click the checklist name. 4. Validate the skill(s)/item(s) under each listed competency by clicking the checkbox to the left of each skill/item. 5. Leave the Date at the default of the current date. 6. Select the appropriate rating for the skill/item from the Rating drop-down options. Note: The option available for any given skill/item are defined at the 7. Repeat steps #4-6 for all competencies on the checklist. 8. Add comments to the checklist by clicking Observation Notes in the upper right corner of the checklist. 9. Enter a comment in the text box. 10. Uncheck the Hide note from employee checkbox. 11. Click Post. | • User: Scott Lang • Checklist: UAT Checklist B | • Observation checklist completed.
12. Associate the comment with the appropriate competency by clicking the Competencies link under the comment. 13. Click the checkbox next to the appropriate competency or competencies. 14. Click Save. 15. Click Back under the navigation pane to the left of the page. 8. Click Submit for Approval to forward the checklist to the user's Manager for approval. 8. Click Save under the navigation pane to the left of the page.
1.2 | MU Checklist Verifier | Add an attachment to an observation checklist | 1. From the Welcome page, place the cursor over the Checklists navigation tab and select Manage Checklists. 2. Under the Search Users heading, locate the appropriate user for whom you will verify a checklist. 3. Click the checklist name. 4. Click the Attachments tab. 5. Click Choose File. 6. Locate the file you wish to attach. Click Open. 7. Click Add. 8. Click Save under the navigation pane to the left of the page. | • User: Rick Jones • Checklist: UAT Checklist A | • Attachment is added to the checklist.
1.3 | MU Checklist Verifier | View an attachment to an observation checklist | 1. From the Welcome page, place the cursor over the Checklists navigation tab and select My Checklists. 2. Click the name of the checklist you wish to view. 3. Click the Attachments tab. 4. Click the name of the attachment you wish to view. 5. Using the Save As window, navigate to the location where you wish to save the attachment. Click Save. 6. Open the file from the saved location. | • Checklist: UAT Checklist A | • UAT_Attachment_1 is viewed.

## MU Manager
User: Reed Richards
Username: rrichards1234
Password: mtrx1234
Division (Company): Matrix Service Company
Testing Security Role: MU Manager
# | Role | Task | Steps | Inputs/Data | Expected Results | Actual Results | Pass/Fail | Date Tested | Questions/Comments (UAT Tester) | Resolution/Notes (Reserved for UAT Admin)
1.1 | MU Manager | Administer an observation checklist | 1. From the Welcome page, place the cursor over the Checklists navigation tab and select Manage Checklists. 2. Under the Search Users heading, locate the appropriate user for whom you will verify a checklist. 3. Click the checklist name. 4. Validate the skill(s)/item(s) under each listed competency by clicking the checkbox to the left of each skill/item. 5. Leave the Date at the default of the current date. 6. Select the appropriate rating for the skill/item from the Rating drop-down options. Note: The option available for any given skill/item are defined at the 7. Repeat steps #4-6 for all competencies on the checklist. 8. Click Save under the navigation pane to the left of the page. | • User: Hank Pym • Checklist: (TEST) Welding | • Observation checklist completed.
1.2 | MU Manager | Approve an observation checklist verified by another user | 1. On the Welcome page, click the Approve Checklists link in the My Training Inbox widget. 2. Click the appropriate checklist name to review the checklist. 3. Scroll to the bottom of the page and click Approve. | • User: Neal Shaara • Checklist: UAT Checklist D | • Observation checklist is approved.
1.3 | MU Manager | Deny an observation checklist verified by another user | 1. On the Welcome page, click the Approve Checklists link in the My Training Inbox widget. 2. Click the appropriate checklist name to review the checklist. 3. Scroll to the bottom of the page and click Deny. 4. Enter comments explaining the denial in the Deny Approval Comments pop-up window. | • User: Daisy Johnson • Checklist: UAT Checklist E | • Observation checklist is denied.
1.4 | MU Manager | Add a co-planner/vertifier to an observation checklist | 1. From the Welcome page, place the cursor over the Checklists navigation tab and select Manage Checklists. 2. Under the Search Users heading, locate the appropriate user and checklist for which you wish to add a co-planner/verifier. 3. Click the checklist name. 4. Click the Co-Planners tab under the Overview heading. 5. Click Add Co-Planner. 6. Enter the last name of the user you wish to add as a Verifier in the Last Name field. 7. Click Search. 8. Click the name of the user. 9. Verify the user appears on the Co-Planners tab. 10. Click Save under the navigation panel to the left of the page. | • User: Jennifer Walters • Checklist: UAT Checklist G | • Co-planner/verifier is added to the observation checklist.
1.5 | MU Manager | Add an attachment to an observation checklist | 1. From the Welcome page, place the cursor over the Checklists navigation tab and select Manage Checklists. 2. Under the Search Users heading, locate the appropriate user for whom you will verify a checklist. 3. Click the checklist name. 4. Click the Attachments tab. 5. Click Choose File. 6. Locate the file you wish to attach. Click Open. 7. Click Add. 8. Click Save under the navigation pane to the left of the page. | • User: Carol Danvers • Checklist: UAT Checklist F | • Attachment is added to the checklist.
1.6 | MU Manager | View an attachment to an observation checklist | 1. From the Welcome page, place the cursor over the Checklists navigation tab and select My Checklists. 2. Click the name of the checklist you wish to view. 3. Click the Attachments tab. 4. Click the name of the attachment you wish to view. 5. Using the Save As window, navigate to the location where you wish to save the attachment. Click Save. 6. Open the file from the saved location. | • Checklist: (TEST) Welding | • UAT_Attachment_1 is viewed.

## MU Default User
User: Danielle Moonstar
Username: dmoonstar1234
Password: mtrx1234
Division (Company): Matrix Service, Inc
Testing Security Role: MU Default User
# | Role | Task | Steps | Inputs/Data | Expected Results | Actual Results | Pass/Fail | Date Tested | Questions/Comments (UAT Tester) | Resolution/Notes (Reserved for UAT Admin)
1.1 | MU Default User | Review a completed observation checklist | 1. From the Welcome page, place the cursor over the Checklists navigation tab and select My Checklists. 2. Click the Show Completed checkbox. 3. Click the name of the checklist you wish to view. 4. Review the validated competencies and associated skill(s)/item(s). 5. Review any comments associated with the checklist by clicking Observation Notes in the upper right corner of the checklist. | • Checklist: UAT Checklist H | • Completed observation checklist is viewed.
1.2 | MU Default User | Review an in progress observation checklist | 1. From the Welcome page, place the cursor over the Checklists navigation tab and select My Checklists. 2. Click the name of the checklist you wish to view. 3. Review the validated competencies and associated skill(s)/item(s). 4. Review any comments associated with the checklist by clicking Observation Notes in the upper right corner of the checklist. | • Checklist: UAT Checklist I | • In progress observation checklist is viewed.
1.3 | MU Default User | Add comments to an observation checklist | 1. From the Welcome page, place the cursor over the Checklists navigation tab and select My Checklists. 2. Click the Show Completed checkbox if you wish to access a completed checklist. 3. Click the name of the checklist you wish to view. 4. Click Observation Notes in the upper right corner of the checklist. 5. Add comments to the checklist entering a comment in the text box. 6. Click Post. | • Checklist: UAT Checklist H (completed checklist) | • Comments are added to an observation checklist.
1.4 | MU Default User | Add an attachment to a checklist | 1. From the Welcome page, place the cursor over the Checklists navigation tab and select My Checklists. 2. Click the name of the checklist you wish to view. 3. Click the Attachments tab. 4. Click Choose File. 5. Locate the file you wish to attach. Click Open. 6. Click Add. 7. Click Save under the navigation pane to the left of the page. | • Checklist: UAT Checklist I | • Attachment is added to the checklist.
1.5 | MU Default User | View an attachment to an observation checklist | 1. From the Welcome page, place the cursor over the Checklists navigation tab and select My Checklists. 2. Click the name of the checklist you wish to view. 3. Click the Attachments tab. 4. Click the name of the attachment you wish to view. 5. Using the Save As window, navigate to the location where you wish to save the attachment. Click Save. 6. Open the file from the saved location. | • Checklist: (TEST) Welding | • UAT_Attachment_1 is viewed.